## Status Report
Project Name | 2 Player Online Games |  | Date |  | 2023-12-09 | Project Manager |  | Ian Jackson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
The project is complete. All of the games we planned to have done for the demo (checkers, connect 4, tic tac toe, othello) are functional. This week was mostly spent on final debugging and UI improvements. Though our product doesn't have every feature we considered when beginnning, it meets the expectations we set for ourselves once we had a better idea of how much we could get done in the time alotted. |  |  |  | Connect-4 |  | 100% | Complete
|  |  |  | Checkers |  | 100% | Complete
|  |  |  | Othello |  | 100% | Complete
|  |  |  | Final Demo |  | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
N/A |  |  | N/A |  |  | Final Demo
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Drew Blackman | Connect4/Testing/UI | 8 | Risk | The project is finished, so no risks are present.
Cal Hargis | Connect4/Tests | 4
Ryan Lee | Checkers/Othello/Frontend | 8
Yiqi Wang | Testing/UI | 6 | Issue | While there were still several bugs at the beginning of the week that would have been an issue during the demo, we have fixed all that we could find in testing and consider the product finished.
Ian Jackson | Checkers/Testing/Backend | 6
Total |  | 32

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task