## Status Report
Project Name | 2 Player Online Games |  | Date |  | 2023-10-21 | Project Manager |  | Ian Jackson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
This week we completed our desired tasks and also finished up a few more. The server can handle several requests related to setting up and connecting to existing game lobbies. Logic for tic-tac-toe is fully implemented, and we've started to lay the ground work for checkers as well. Tic-tac-toe has a working GUI on the front end. We've begun implementing integration tests to run next week, and are on track to have our planned features ready by the first demo. |  |  |  | Tic-tac-toe Logic |  | 100% | Complete
|  |  |  | Tic-tac-toe Basic GUI |  | 100% | Complete
|  |  |  | Lobby Creation and Client Connection |  | 100% | Complete
|  |  |  | Integration Testing |  | 30% | On Track
|  |  |  | Checkers Implementation |  | 10% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Tic-tac-toe logic and GUI, lobby creation, client connection |  |  | N/A |  |  | Integration testing
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Drew Blackman | Backend+Diagram+Meeting | 4 | Risk | All task are currently on track, so the only current risk is that the time required to complete future tasks has been underestimated.
Cal Hargis | Backend+Meeting | 2
Ryan Lee | Frontend+Diagram+Meeting | 2.5
Yiqi Wang | Frontend+Meeting | 1.5 | Issue | Many of our tasks are coming along faster than anticipated. As a result we are filling fewer hours than planned and there is the possibility that we will run out of things to do well before the first demo. If this happens we may need to move up other tasks and consider adding new features.
Ian Jackson | Backend+Report+Meeting | 4
Total |  | 14

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task