## Status Report
Project Name | 2 Player Online Games |  | Date |  | 2023-10-28 | Project Manager |  | Ian Jackson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
This week we sucessfully got our prototype into production on a live website. With this done, our primary focus was on testing the prototype to ensure it was ready for the first demo next week. This consited of manual testing and automated testing, which we developed a simple framework for. With that going well we also decided to begin work on features for the next demo. This work consited primarily of developing new back-end logic for future games. |  |  |  | Link Creation and Sharing |  | 100% | Complete
|  |  |  | Setup on Production Server |  | 100% | Complete
|  |  |  | Testing |  | 100% | Complete
|  |  |  | Connect-4 Implementation |  | 10% | On Track
|  |  |  | Checkers Implementation |  | 10% | On Track
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Live on production server, link sharing, prototype testing |  |  | N/A |  |  | Checkers and Connect-4 Implementation
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Drew Blackman | Framework+Testing+Meeting | 6 | Risk | All task are currently on track, so the only current risk is that the time required to complete future tasks has been underestimated.
Cal Hargis | Testing+Backend+Meeting | 2
Ryan Lee | Links+Sockets+Meeting | 3
Yiqi Wang | UI+Testing+Meeting | 4 | Issue | No serious issues are present at this time. Work is ahead of schedule, the prototype is ready to demo, and many of the features that we anticipated having the most trouble with have been successfully implemented.
Ian Jackson | Backend+Testing+Meeting | 3.5
Total |  | 18.5

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task