## Status Report
Project Name | 2 Player Online Games |  | Date |  | 2023-11-11 | Project Manager |  | Ian Jackson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
As of this week we have our first version of checkers running in the application with some custom design elements and basic user interaction. Work is continuing with improving the user interface and testing the backend logic. Connect-4 is not far behind, with the backend logic coming along well and many frontend design elements completed. In an effort to make sure that everyone has something to be doing, we have also tenatively added Othello as another game, and initial work on its implementation has begun. Overall the project continues to be on track and no serious impediments have been encountered. |  |  |  | Connect-4 Backend |  | 60% | On Track
|  |  |  | Connect-4 Frontend |  | 50% | On Track
|  |  |  | Checkers Backend |  | 80% | On Track
|  |  |  | Checkers Frontend |  | 60% | On Track
|  |  |  | Othello Implementation |  | 5% | On Track
|  |  |  | Demo 2 |  | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
First version of checkers implemented |  |  | N/A |  |  | Demo 2
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Drew Blackman | Backend/Meeting/Reading | 4 | Risk | As with weeks prior, we do not see any serious risks at this time. The only possible risk would seem to be that of falling short of our deadlines by not working towards them consistently, and everyone on the team continues to do their part to avoid that.
Cal Hargis | Backend/Meeting/Reading | 4
Ryan Lee | Frontend/Meeting | 6
Yiqi Wang | Frontend/Design/Reading | 5 | Issue | No issues to report at this time. The project is on schedule and there seems to be no obvious threat to that currently.
Ian Jackson | Backend/Meeting/Reports | 5
Total |  | 24

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task