## Status Report
Project Name | 2 Player Online Games |  | Date |  | 2023-11-18 | Project Manager |  | Ian Jackson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
While this week did not see the completion of as many large milestones as previous weeks, it did see significant progress in the tasks we intend to have finished in time for the next demo. Checkers is nearly complete, with the front end being polished up and the back end going through some debugging. Connect 4 is a little further behind, but again the backend is mostly present and the frontend is going well. Significant progress has also been made on Ohtello, a feature we didn't initially intend to have ready for demo 2 but which might be ready by then as well. |  |  |  | Connect-4 Backend |  | 80% | On Track
|  |  |  | Connect-4 Frontend |  | 70% | On Track
|  |  |  | Checkers Backend |  | 95% | On Track
|  |  |  | Checkers Frontend |  | 80% | On Track
|  |  |  | Othello Implementation |  | 45% | On Track
|  |  |  | Demo 2 |  | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
N/A |  |  | N/A |  |  | Demo 2
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Drew Blackman | Backend/Code Review/Meeting | 7 | Risk | We hope to have as much of the features planned for demo 2 done before Thanksgiving break as possible, since putting in consistent work during that time will be difficult. We're getting a little close to that deadline, so there is a risk that not everything will be done before then.
Cal Hargis | Backend/Code Review/Meeting | 5
Ryan Lee | Frontend/Code Review/Meeting | 4
Yiqi Wang | Frontend/Code Review/Meeting | 5 | Issue | Despite the above risk, there are no issues present at this time. Overall the project continues to progress smoothly.
Ian Jackson | Frontend/Code Review/Meeting | 5
Total |  | 26

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task