## Status Report
Project Name | 2 Player Online Games |  | Date |  | 2023-10-14 | Project Manager |  | Ian Jackson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
This week we made layed out a specific timeline for accomplishing required tasks, as represented in the PERT and Gantt charts. The frontend team worked on mock-ups in figma and began work on the tic-tac-toe display. They also worked with the backend team to set up connections between the client and server. The backend team began creating the http server that will host games, and set it up to create a lobby for multiple clients to connect to. This work will continue into next week, as will implementation of necessary tic-tac-toe logic on both the front and back end. |  |  |  | Tic-Tac-Toe Display |  | 80% | On Track
|  |  |  | Server Creation |  | 100% | Complete
|  |  |  | Lobby Creation and Client Connection |  | 25% | On Track
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Server Creation |  |  | N/A |  |  | Implement Tic-Tac-Toe Logic
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Drew Blackman | Backend Dev + Meeting | 6.5 | Risk | All task are currently on track, so the only current risk is that the time required to complete future tasks has been underestimated.
Cal Hargis | Backend Dev + Meeting | 2.5
Ryan Lee | Frontend Dev + Meeting | 5
Yiqi Wang | Figma + Meeting | 2 | Issue | N/A
Ian Jackson | Charts/Report + Meeting | 2.5
+ Backend Dev
Total |  | 18.5

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task