## Status Report
Project Name | 2 Player Online Games |  | Date |  | 2023-11-04 | Project Manager |  | Ian Jackson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
This week we successfully demoed our prototype with a working tic-tac-toe service. We've now begun more focused work on new features with checkers and connect-4, as well as making some small improvements to tic-tac-toe. The work is pretty evenly divided, one person each for the front end of checkers and connect-4, and another person each for their respective backends, and our final member working on server protocol. We're on track and not facing any serious risks. |  |  |  | Prototype Demo |  | 100% | Complete
|  |  |  | Connect-4 Implementation |  | 20% | On Track
|  |  |  | Checkers Implementation |  | 30% | On Track
|  |  |  | Tic-Tac-Toe Improvements |  | 100% | Complete
|  |  |  | Demo 2 |  | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Prototype demo |  |  | N/A |  |  | Demo 2
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Drew Blackman | WebServer/Backend | 2 | Risk | We hope to have the new games we are working on at least in working prototype form by the next demo in a few weeks. This should be achievable, but could be an easy mark to miss if consistent progress isn't made.
Cal Hargis | Backend/Testing | 2
Ryan Lee | Frontend/Testing/Meeting | 3.5
Yiqi Wang | Frontend/Scripts/Meeting | 4 | Issue | No serious issues are present at this time. Work is on-track and we aren't currently aware of any serious risks that could jeopardize the project.
Ian Jackson | Backend/Meeting/Reports | 4.5
Total |  | 16

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task