## Status Report
Project Name | 2 Player Online Games |  | Date |  | 2023-11-25 | Project Manager |  | Ian Jackson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Progress on this week was notably less than weeks past, both due to having a midterm to work on and most of our team being out of town or otherwise busy for the holiday. Some small improvements were made, but overall it seems we were a little too optimistic in our ability to tie up all of the loose ends we wanted to this week. We will still have plenty to show at the next demo, but not quite as much as originally planned. |  |  |  | Connect-4 Backend |  | 80% | Delayed
|  |  |  | Connect-4 Frontend |  | 70% | Delayed
|  |  |  | Checkers Backend |  | 95% | On Track
|  |  |  | Checkers Frontend |  | 80% | Delayed
|  |  |  | Othello Implementation |  | 45% | On Track
|  |  |  | Demo 2 |  | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
N/A |  |  | N/A |  |  | Demo 2
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Drew Blackman | Study/Midterm | 3 | Risk | The project is delayed in some areas. These delays are not too serious and should be caught up fairly quickly, but there is a real danger of the project slipping further behind.
Cal Hargis | Study/Midterm | 3.5
Ryan Lee | Midterm/Frontend | 3.5
Yiqi Wang | Frontend/Midterm/Design | 7 | Issue | Connet-4 is behind schedule. Checkers is slightly behind as well, but its frontend is nearly ready and the backend is working but still in need of optimization. However, both are still far enough along that they should be fully ready in time for the final demo.
Ian Jackson | Backend/Report/Midterm | 4.5
Total |  | 21.5

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task