## Status Report
Project Name | 2 Player Online Games |  | Date |  | 2023-09-30 | Project Manager |  | Ian Jackson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
This week we established team roles and created an initial plan for the architecture of the project. It will be a web application with the the frontend written using Vue and the backend written using Golang. We plan to create an initial framework to handle online communication between players which we can then build various games on top off. Aside from individuals taking time to learn the languages we will use, the only goal this week was to create the org chart. |  |  |  | N/A |  | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Org Chart
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Drew Blackman | Architecture desing | 2 | Risk
Cal Hargis | Learning Golang | 0.5
Ryan Lee | Frontend Research | 1.5
Yiqi Wang | Frontend, UI/UX Research | 1 | Issue | .
Total |  | 5

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task